## Comms and Signals
Phase 1 | MP | Location Name | Estimated Cost | Quarter | Calendar Year of Upgrade | Phase 2 | MP | Location Name | Estimated Cost | Quarter | Calendar Year of Upgrade | Phase 3 | MP | Location Name | Estimated Cost | Quarter | Calendar Year of Upgrade
Design | 9.1 | Control Point True | 50000 | Q1 | 2026 | Design | 19.89 | Control Point Kennedy | 51000 | Q2 | 2026 | Design | 30.22 | Auto 5 | 45000 | Q3 | 2027
Design | 10.6 | Control Point Tower (Remote) | 50000 | Q1 | 2026 | Design | 22.3 | Auto 3 | 51000 | Q2 | 2026 | Design | 30.68 | Broadway Crossing | 45000 | Q3 | 2027
Design | 10.75 | Control Point Tower (Main) | 50000 | Q1 | 2026 | Design | 24.7 | Auto 4 | 51000 | Q2 | 2026 | Design | 31.9 | Simpsons Rd Crossing | 45000 | Q3 | 2027
Material | 9.1 | Control Point True | 150000 | Q2 | 2026 | Material | 19.89 | Control Point Kennedy | 250000 | Q1 | 2027 | Material | 30.22 | Auto 5 | 150000 | Q1 | 2028
Material | 10.6 | Control Point Tower (Remote) | 200000 | Q2 | 2026 | Material | 22.3 | Auto 3 | 150000 | Q1 | 2027 | Material | 30.68 | Broadway Crossing | 200000 | Q1 | 2028
Material | 10.75 | Control Point Tower (Main) | 200000 | Q2 | 2026 | Material | 24.7 | Auto 4 | 150000 | Q1 | 2027 | Material | 31.9 | Simpsons Rd Crossing | 200000 | Q1 | 2028
Construction | 9.1 | Control Point True | 375500 | Q3 | 2026 | Construction | 19.89 | Control Point Kennedy | 400000 | Q1 | 2027 | Construction | 30.22 | Auto 5 | 400000 | Q1 | 2028
Construction | 10.6 | Control Point Tower (Remote) | 375500 | Q3 | 2026 | Construction | 22.3 | Auto 3 | 400000 | Q1 | 2027 | Construction | 30.68 | Broadway Crossing | 400000 | Q1 | 2028
Construction | 10.75 | Control Point Tower (Main) | 375500 | Q3 | 2026 | Construction | 24.7 | Auto 4 | 400000 | Q1 | 2027 | Construction | 31.9 | Simpsons Rd Crossing | 400000 | Q1 | 2028
Design | 12.9 | Control Point Ford | 50000 | Q2 | 2026 | Design | 26.8 | Control Point Eva (Main) | 51000 | Q3 | 2026 | Design | 32.44 | Control Point Moore | 45000 | Q4 | 2027
Design | 15.2 | Auto 1 | 50000 | Q2 | 2026 | Design | 26.81 | Main St Crossing | 51000 | Q3 | 2026 | Design | 32.6 | Rodeo Dr Crossing | 45000 | Q4 | 2027
Design | 17.8 | Auto 2 | 50000 | Q2 | 2026 | Design | 26.95 | Control Point Eva (Remote) | 51000 | Q3 | 2026 | Design | 32.65 | North St Crossing | 45000 | Q4 | 2027
Material | 12.9 | Control Point Ford | 150000 | Q3 | 2026 | Material | 26.8 | Control Point Eva (Main) | 150000 | Q2 | 2027 | Material | 32.44 | Control Point Moore | 150000 | Q2 | 2028
Material | 15.2 | Auto 1 | 200000 | Q3 | 2026 | Material | 26.81 | Main St Crossing | 200000 | Q2 | 2027 | Material | 32.6 | Rodeo Dr Crossing | 200000 | Q2 | 2028
Material | 17.8 | Auto 2 | 200000 | Q3 | 2026 | Material | 26.95 | Control Point Eva (Remote) | 200000 | Q2 | 2027 | Material | 32.65 | North St Crossing | 200000 | Q2 | 2028
Construction | 12.9 | Control Point Ford | 375500 | Q4 | 2026 | Construction | 26.8 | Control Point Eva (Main) | 400000 | Q2 | 2027 | Construction | 32.44 | Control Point Moore | 400000 | Q2 | 2028
Construction | 15.2 | Auto 1 | 375500 | Q4 | 2026 | Construction | 26.81 | Main St Crossing | 400000 | Q3 | 2027 | Construction | 32.6 | Rodeo Dr Crossing | 400000 | Q3 | 2028
Construction | 17.8 | Auto 2 | 375500 | Q4 | 2026 | Construction | 26.95 | Control Point Eva (Remote) | 400000 | Q3 | 2027 | Construction | 32.65 | North St Crossing | 400000 | Q3 | 2028

## TS Program Est
All materials and construction
VPRA Work List |  |  |  | No design
|  |  | ROM Cost | Guessing on timing & nominal dollars only
Curve Rail Replacement |  | Timber & Surfacing (T&S) |  | State FY27 | State FY28 | State FY29 | State FY30 | State FY31 | State FY32 | Total
MP 17.4 M1 | FY27 | M1 / M2 MP 15 - 32.50 | Curve Replacement | 600000 |  | 600000 | 600000 | 600000 |  | 2400000
MP 29.1 M2 | FY27 |  | T&S |  |  |  | 3500000 | 3500000 |  | 7000000
MP30 M1 | FY29 |  | Stations Tie Replacement | 1357000 | [5 empty] | 1357000
MP 29.1 M1 | FY29 | Stations Tie Replacement: | TO Replacement | 80000 | 1050000 | 600000 |  |  |  | 1730000
MP 21.5 M2 | FY30 | Main Street Sta M1 32.6 | [7 empty] | 0
MP 19.4 M1 | FY30 | Central Sta M1 30.5
MP 15.3 M1 | FY31 | Mall Center Sta M1 21.4 | [7 empty] | 12487000
MP 14.3 M1 | FY31 | Rail Road Sta M1 19.15
Union Sta M1 15.0
|  |  | Mainline 1 (M1) Track Miles (TM) | 17.5
|  |  | Mainline 2 (M2) TM | 17.5
|  |  | Total TM | 35
|  |  | T&S Cost/TM | 200000
|  |  | Total T&S cost | 7000000
Turnout Replacement (TO)
Burke House Tk MP 19.8 M1 |  |  | Cost per TO | 150000
GPO Lead MP 16.7 M1 |  |  | Industry lead TO cost | 600000
Gas Tk MP 18.2 M2
Maryland Power MP 27.25 M2
CP Moore x2 MP 32.44, M1 and M2 |  |  | Estimated Cost per curve | 300000
CP Ford x4 MP 12.9, M1 and M2
CP Tower, No 6 TO, MP 10.7, M2 to Horn

## 6YR Structures
6-YEAR PROJECTION OF BRIDGE COSTS | [6 empty] | Phase Colors: |  |  | 2026-03-17
Design
LINE SEGMENT: 9.25 to 32.75 | [6 empty] | Construction w/ Materials
6-YEAR CAPITAL & MAINTENANCE PROGRAM
| Bridge TIE DECK RENEWALS |  |  | CULVERT Replacement |  | BRIDGE REPAIRS / REPLACEMENTS |  |  | YEAR TOTAL
YEAR | MP | # of Ties | CAPITAL | MP | CAPITAL | MP | DESCRIPTION | CAPITAL | CAPITAL
2026-2027 |  |  | 0 | 9.6,22.6,23.6, 31.3, 31.8 | 200000 |  |  | 0 | 200000
2027-2028 |  |  | 0 | 9.6 | 300000 |  | Engineering - 10.3 & 16.9 - retaining structures | 120000 | 1195000
|  |  |  | 22.6 | 325000
|  |  |  | 23.6 | 450000
2028-2029 |  |  | 0 | 31.3 | 200000 | 10.3 | Install Ballast retainers | 300000 | 1125000
|  |  |  | 31.8 | 300000 | 16.9 | Install wingwall / retaining wall | 175000
[6 empty] | 13.1 & 28.8 | Concrete Encasemet/Rehabilitation - Engineering | 150000
2029-2030 | 16.9 | 884 | 1000000 |  |  | 13.1 & 28.8 | Concrete Encasemet/Rehabilitation | 1500000 | 2500000
2030-2031 | 28.8 | 254 | 287330.3167 |  |  | 15 | Span Replacement - Engineering | 190000 | 627330.3167
[6 empty] | 9.9, 10.2 | Steel repairs - Engineering | 150000
2031-2032 |  |  | 0 |  |  | 9.9, 10.2 | Steel repairs | 1000000 | 6500000
[6 empty] | 15 | Span replacements | 5500000
6 YR. |  |  | 1287330.3167 |  | 1775000 |  |  | 9085000 | 12147330.3167
TOTAL
6 YR. |  |  | 257466.0633 |  | 355000 |  |  | 1817000 | 2024555.0528
AVG.
Per tie deck renewal |  |  | 1131.2217